|  | Goals | Actions Related To Goals | Specific Planning | Resources Needed |
| --- | --- | --- | --- | --- |
| June 06 | Meet with administration | Share LICT work to date and draft plan Include LICT in School Development Plan |  | Continuum (student-friendly and other) Sample report cards Planning calendar |
| Sept 06 | Introduce New Role of Technology Dept. Head | Informal introduction of role of technology dept. head |  |  |
| Oct 06 | Mentoring of teachers for LICT |  | Judy to check teacher timetables for mentoring purposes Judy to work with teachers on an individual basis to assess teachers’ uses and needs |  |
| Nov 06 | WBJE introduced to LICT – Nov.16 LICT Team meets to discuss progress and follow-up – Nov.1 | Publish article in Gray Gazette re : LICT (for report cards) | Continuation of Oct. Scheduled meetings one-on-one and/or grade level to discuss needs and uses (follow-up to class visits) |  |
| Dec 06 | Intro to whole staff at staff meeting | Discuss format of student assessment Discuss purposeful use of ICT to support student achievement in all subject areas Introduce developmental continuum | Introduce goals/objectives of LICT wilth grade level teachers | Continuum Report cards Only for small groups |
| Jan 07 | Introduce LICT with Dept. Heads |  | Grade 5 and 6 teachers meet with Judy | Eportfolio (Student Demo) |
| Feb 07 |  |  |  | ePortfolio with students Grades 5 and 6 |
| Mar 07 | Practise assessment using developmental continuum Publish article for parent in Gray Gazette | Discuss format of assessment Teacher self-assessment |  | Continuum Eportfolio |
| Apr 07 | Intro to continuum and 3 year implementation Grade 4 - 6 | Discuss format of student assessment Discuss purposeful use of ICT to support student achievement in all subject areas Introduce developmental continuum Teacher self-assessment | Online needs assessment Introduce LICT website and associated resources (including FirstClass conference) | Continuum Gr 7 and 8 assessment form Eportfolio |
| May 07 | Introduce LICT with grade 4 teachers LIC T team meets to finalize plans for 2007-08 Feedback from teachers | Changes to report cards, grades 4 -6 Discuss plans for K-3 assessment |  | K– 8 report cards |
| June 07 | Plans for LICT 07-08 to be put in school plan New Report Card Goes Home Gr.4-6 | New assessment for grades 7 and 8 Support teachers with assessment |  |  |
| 2007-08 December 2007 | Implementation of report cards for grades 5 and 6 Beginning work with K-2 groups for LICT assessment |  | Discuss assessment with teachers grades K-3, 7-8 Introduce goals/objectives of LICT with grade level teachers |  |
| March 2008 | Introduce LICT with grade 7 and 8 teachers. Evaluation of progress to date |  |  |  |
| April/May 2008 | LwICT team meeting LwICT admin meeting |  |  |  |
| June | Report card template for grades 7 and 8 |  |  |  |
| 2008-2009 |  |  |  |  |
| September | Inservice teachers 2 -8 |  |  |  |
| November 2008 | Making parents aware of LICT |  |  |  |