SJR Junior School

3 Year Plan to implement

Literacy with ICT Continuum

Junior School

Year 1

Pilot Team: technology specialist (Roland Buduhan) and grade-team leaders Carla Brown (k-1), Tracey Gluska (2-3), Alison Elkins (4-5), Noella Fontaine (French k-2), Carolyn Berthelet (French 3-5)

Involving partners/stakeholders: principal, technology-specialist, grade-team leaders, teachers, students, parents

Identify resources: Literacy with ICT webpage, WebCT, computer teachers, network of independent schools ICT teachers, ManACE,

Implementation process YEAR 1:

- Pilot team will be involved in planning learning activities, projects, student assessment, student self-assessment to report their students’ progress in the Literacy with ICT continuum.  All resources they create will be saved in a shared folder

- Grade-team leaders, through discussions with their teams, will create a draft of report card changes that reflect their use of the Literacy with ICT continuum (will be used in year 2)

- Grade-team leaders will share their progress with their teams during their regularly scheduled team meetings

- Each grade-team leader will do on-going assessment of three students

- Technology specialist teacher will assist Grade-team leaders in implementing the document

- (Roland) Create on-line learning community (Web-CT) to share resources

Meeting time required: once a month, lunch-time meetings

- PD required for team leaders in Literacy with ICT:

- SAG, Evergreen School Division’s “Riding the Wave of Change”, ManACE

Topics to discuss and review each month of 2006-2007

Introduction to the continuum documents (September)

Inquiry based lesson planning (October)

Higher level thinking skills, Bloom’s taxonomy (November)

Student self reflection – Assessment as learning (December)

Assessment for learning – techniques and strategies (January)

E-Portfolios (February)

Assessment of learning: Report Card changes (March)

Parent information (April)

Planning for next year (May, June)

Year 2

Junior School: Select grades (1, 3, 5) will implement student assessment of Literacy with ICT skills

- Include report card changes in these grades

- These teachers will use assessment tools created in year-1

- Pilot-team members from Year 1 will serve as mentors

PD sessions must be planned throughout the year focusing on:

Literacy with ICT, Constructivism, Inquiry-based learning

Update and train team members on upcoming release of the Parent Handbook

- How will SJR communicate this to parents and students? Possibilities include: Eagle Eye (school e-newsletter) Junior School technology blog, Parents Association

Review current reporting procedures.  Possible idea:

- Change each term’s report card to focus on a different “Big Idea” from the continuum.  Example: Term 1 can focus on Plan & Focus, Term 2 could focus on Produce to Show Understanding

Update team members on the following documents from the Dept. of Education:

- Independent-Together

- Communicating Student Learning

Update all staff on following topics:

- Features in ePearl such as workspace, parent feedback, inter-class sharing, version 3 summer release

- Assessment: communicate full picture: growth, progress, achievement

- Curriculum Navigator (to be  released this year)

Hardware/Infrastructure updates: Kindergarten-Grade 1 classrooms to receive SMART board and projector in each classroom.  Kindergarten-Grade 3 to receive 6 wireless laptops each.  Grade 4-5 classrooms to receive newer workstations in the classrooms.  Grade 4/5 video cameras to be installed in 5VS, 4CK, with firewire port on their SMART board computers.

All laptops/workstations in Junior School to all run Windows XP, which includes MovieMaker and Photostory

Ensure all students, Kindergarten-Grade 5 have accounts in ePearl.

Ensure server space is prepared for memory requirements of ePearl.

Year 3

JS:	100% teacher participation in implementing the Literacy with ICT skills

All JS reports will be edited to include assessment of Literacy with ICT skills

Grade 1, 3, 5 teachers from year-2 will serve as mentors

Assess, monitor, and revise current teaching practices, reporting methods, and assessment techniques.  Evaluate at end of year to plan for Year 4.  Possible directions:

Change report cards to an infused model of reporting Literacy with ICT

Possibility of one-to-one computing

Investigate other means of online collaboration through blogs, wikis, etc.

Partnerships with other schools with online collaboration projects