SJR Junior School

3 Year Plan to implement

Literacy with ICT Continuum

Junior School

Year 1

Pilot Team: technology specialist (Roland Buduhan) and grade-team leaders Carla Brown (k-1), Tracey Gluska (2-3), Alison Elkins (4-5), Noella Fontaine (French k-2), Carolyn Berthelet (French 3-5)

Involving partners/stakeholders: principal, technology-specialist, grade-team leaders, teachers, students, parents

Identify resources: Literacy with ICT webpage, WebCT, computer teachers, network of independent schools ICT teachers, ManACE,

Implementation process YEAR 1:

- Pilot team will be involved in planning learning activities, projects, student assessment, student self-assessment to report their students’ progress in the Literacy with ICT continuum. All resources they create will be saved in a shared folder

- Grade-team leaders, through discussions with their teams, will create a draft of report card changes that reflect their use of the Literacy with ICT continuum (will be used in year 2)

- Grade-team leaders will share their progress with their teams during their regularly scheduled team meetings

- Each grade-team leader will do on-going assessment of three students

- Technology specialist teacher will assist Grade-team leaders in implementing the document

- (Roland) Create on-line learning community (shared folder and Moodle) to share resources and communicate

Meeting time required: once a month, lunch-time meetings, plus 2 afternoon meetings to plan report card changes, EPortfolios, parent communication

PD required for team leaders in Literacy with ICT:

SAG, Evergreen School Division’s “Riding the Wave of Change”, ManACE

Organize laptop locations and computer lab schedule to best meet the needs of all grades

Topics to discuss and review each month of 2006-2007

Introduction to the continuum documents (September)

Inquiry based lesson planning (October)

Higher level thinking skills, Bloom’s taxonomy (November)

Student self reflection – Assessment as learning (December)

Assessment for learning – techniques and strategies (January)

E-Portfolios (February)

Assessment of learning: Report Card changes (March)

Parent information (April)

Planning for next year (May, June)

Year 2

JS: Select grades (1, 3, 5) will implement student assessment of Literacy with ICT skills: each grade start the year with student goal setting, and ePortfolio setup

communicate to parents through: "Meet the teacher evening", parent portal, articles in EagleEye (school newsletter), and school website

Include report card changes in these grades

These teachers will use assessment tools created in year-1

Pilot-team members from Year 1 will serve as mentors

PD sessions must be planned throughout the year focusing on:

Literacy with ICT, Constructivism, Inquiry-based learning

Year 3

JS: 100% teacher participation in implementing the Literacy with ICT skills

All JS reports will be edited to include assessment of Literacy with ICT skills

Grade 1, 3, 5 teachers from year-2 will serve as mentors