LITERACY WITH ICT IMPLEMENTATION PLAN – 2006-2007

Team Leaders:  		John Cox

Helen Dawert

Christine McInnis

Laurie-Anne Regula

Taras Veryha

Resources:			Cheryl Prokopanko, MECY consultant (for team leaders)

Literacy with ICT online learning community (for team leaders)

Literacy with ICT website www.edu.gov.mb.ca/ks4/tech/tfs/index.html

Timeline:

| Date | Action | Responsibility | Resources |
| --- | --- | --- | --- |
| Mid May  | Report Card Revision | John Cox School Team | Existing report card Continuum |
| Mid May  | Communicate Implementation Plan to Teachers | John Cox ICT Team | Implementation Plan Continuum Learning Experiences |
| June (not completed) | Staff Needs Survey | Helen Dawert | Survey/Rubric |
| Summer 2006 (not complete) | Timetable Scheduling | John Cox Helen Dawert | Timetables |
| Summer 2006 (not addressed) | Fall in-service will be planned | In-service Planning Team | Cheryl Prokopanko |
| Summer 2006 (partial) | Continuum Review | Staff | Continuum |
| Fall 2006 (by end of November) | Continuum Check-in (Learning Experiences, and Continuum implementation discussion) | Staff (ICT teaming-websites) once | Learning Experiences Continuum |
| February 2007 (monthly meetings scheduled) | ICT Action Research Team Meetings | Implementation Team |  |
| Winter 2007 LWICT ePearl/blog | ePearl Practice: Goals, Criteria, Descriptive Feedback and Reflection | Helen Dawert Taras Veryha | Literacy with ICT Cheryl Prokopanko |
| Winter 2007 (by end of March) | Continuum Check-in (Learning Experiences, and Continuum implementation discussion) | Staff | Learning Experiences Continuum |
| Spring 2007 April Inservice | ePearl Powerpoint, discussion | Helen Dawert Taras Veryha | First Class/ePearl |
| Spring 2007 | Inform Tech-team about ePearl/Blog implementation | Helen Dawert | First Class/ePearl |
| Spring 2007 (May) | Attend ICT crash Course for staff members, John | Staff | Cheryl Prokopanko |
| May 2007 | Send Taras and Helen to the Wave of Change Conference, Gimli (Taras did not attend) | Taras Veryha Helen Dawert | Wave of Change |
| Spring 2007 (by end of May) | Continuum Check-in (Learning Experiences, and Continuum implementation discussion) | Staff | Learning Experiences Continuum |
| 2006-2007 (not established) | Peer Coaching investigation | ICT Team | Peer Coaching Other mentoring models |
| 2007/2008 | Establish PD days for teachers regarding LwICT, ePearl | Staff | LwICT Continuum ePearl |
| June 2007 | Peer Coaching Reporting and Decision Making for 2007-2008 School Year | ICT Team Staff | Peer Coaching Report Other mentoring models reports |
| June 2007 | Staff Needs Survey (incomplete) | Helen Dawert | Survey/Rubric |
| September 2007 | E-Pearl Pilot project with Concordia University, Grade 4’s | Taras Veryha |  |
| 2007-2008 | Peer Coaching or alternative implementation |  |  |
| February 2008 | Report to Staff regarding LwICT Winter Session, Parent Handbook launch make accessible for staff review, E-Pearl progress, Google doc’s | Taras/Helen | Notes |
| February 2008 | Reporting of all three categories on all report cards | John/Staff | Reference to ICT, parent handbook |
| February 2008 | Copyright issues for Images/Photos/Video Clips Five rules to remember | Taras/Helen | Lwict /wikispaces |
| February 2008 | Purchase of Smart Board | John/Helen |  |
| April 2008 | E-pearl implementation sessions | Staff |  |
| May 2008 | Parent Handbook available to staff for review | John | Letter for Staff |
| September 2008 | Parent Handbook available for parents in the Fall | John | Letter for parents |

NOTE:  Use Planning BLM-17 – Implementation Plan Checklist, to verify that you have included all information needed.