St. Emile School Implementation Plan

for LwICT during 2006-07

1. LwICT Implementation Team:

1.1 Composition of our LwICT team

One school administrator (Bill), one consultant (Jean), one technical support (Ted), one classroom teacher (Donna) currently. May sessions would include Cathy Holmes, Cathy Caron, Paula Dorsey, and Bill. Fall sessions to include Cheryl, Carol Ann, Ted, Debbie, Linda, Rosemary. Shelley H.’s sessions in fall. Info. to follow. MFIS session.

1.2 Role of our team in LwICT implementation

Info gathering and sharing to staff at meetings.

1.3 Release time for our team this school year to meet and plan and to provide professional learning or mentoring

]

Total of eight days over the two sessions (March and May). For fall session, there is MFIS session and we’ll send six people @ two days each.

1.4 What tips does your team have for how to structure an effective LwICT implementation team?

Approach has to be school wide; provide time to implement with mixture of all levels of team.

2. Professional Learning:

2.1 Schedule and type of professional learning opportunities our LwICT team provided, or are planning to provide, for teachers and school leaders in your division.

March, May and Fall 2007 (MFIS.)

2.3 Types of professional learning (face-to-face, by distance, large group, small group, by grade level or snapshot grouping, one-on-one mentoring…)

Primarily small group (Grade 3 and up).

2.4 Tips our team has for how to structure effective professional learning to support implementation of LwICT

Prioritize our PD days to include Literacy w ICT: included as school goal for 2007-2008. Realistically, wait until balance of staff inserviced in May and fall. When goal setting on April 9th, dedicate a portion of PD days to LwICT. Changes to report card also needed. Letter to parents informing of changes. Research and obtain samples from other schools of how they reported to parents (2007 -2008). Implement for Sept. 2008 across grade levels. Will it be an insert, own section on report cards, each subject area, or just one area? Shelley had several examples to view. Have Dept. Reps. come to inservice us.

3. Implementation Schedule:

3.1 How our teachers have begun to implement LwICT in 2006-07?

All teachers have a copy of the Model document. Teachers will read a portion of the Model document and jigsaw back to entire group regarding contents.

3.3 How our school has included LwICT in our school plans

Was in our school plan to begin the study of the document. Will include in April planning.

3.4 Our projected implementation for 2007-08

All staff inserviced by Fall 2007 in initial implementation; project to use one or two PD days in 2007-2008, inviting MECY to assist us; prepare reporting format for school.Tutorial through KIT 101, other resources.

3.5 Tips our team has for ensuring an effective schedule for implementation of LwICT

Think in small steps, realistic goals.

4. Connections:

4.1 Other school or divisional initiatives that we are connecting to our implementation of LwICT (ie assessment, curriculum [specify], inquiry, etc).

MFIS, CSC, AWCS (divisional goals).

4.2 Tips our team has for effective connection of implementation of LwICT with existing school and/or divisional priorities

Make it priority, don’t over commit. Set aside PD days and document accordingly.

5. Evidence:

5.1 Evidence we are using to support our reporting of student literacy with ICT (portfolios, eportfolios such as ePearl, student profiles, student/teacher conversations, etc

Grade 8 do Powerpoint portfolios, Grades 6 – 8 post assignments on Homepage, e-mail opportunities from parents.

6. Reporting:

6.1 When, how, and who in our school has already reported, or are planning to report, to parents on student literacy with ICT? [Please post your EY and MY reporting model(s) in First Class.]

Not yet determined

6.3 How our reporting on student literacy with ICT is integrated with existing reporting

Not yet determined

7. Parental Reaction:

7.1 Response we have had from parents about the LwICT implementation and ePearl pilot in our school

Not yet determined

8. Learning Tools:

8.1 Do students in our school have access to their own email?

No, looking at it for Middle Years.

8.2 Do students in our school have access to blogs, wikis, and the read/write web?