| Literacy with ICT Team Action Plan VERSION #3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 2006/2007 |  |  |  |  |  |
| Action # | Action Details | Action Owner |  | Progress/Completed Yes/No |  |
| 1 | Assess all teachers for computer literacy using the 2 surveys. Jacqui to create a report based on the survey results. Make suggestions as to IT training for 2007/2008. | JK & BVW |  | This is from the Website JK to download, print and issue. All staff to complete by end of February. Distributed but JK needs to collect information and graph the results to plan the PD Day. |  |
| 2 | All Literacy team members to try 1 learning experience before January/February 2007, from the Government website. | All |  | E-Pearl – got accounts set up. Need to distribute pack of information. Jacqui K (Grade 8’s): All permission letters received and all Grade 8’s have been issued user names and passwords. We have started ePearl. Cheryl B (Grade 5’s): Has completed a weather report on Powerpoint with her class and the internet. Leanne (Grade 6’s): Completed a presentation on powerpoint for the science fair. Yoanne (Grade 1’s): Completed a short story in Word and Paint. |  |
| 3 | Barb and Jacqui to attend the Winter Literacy with ICT Workshop on March 6th & 7th. Jacqui to ask Giuseppi and Cheryl. | JK, BVW and GC |  | JK to email Cheryl to confirm both Barb and Jacqui will attend. GC to book subs. COMPLETED |  |
| 4 | An in-house PD Day to discuss progress, check plan of learning experiences and create a reporting strategy to try in 2007/2008. | JK & GC |  | This will happen in Early April. Print examples of reports before Spring Break for people to review and get ideas. GC gave Jacqui examples of reports from other schools. |  |
| 6 | Based on the survey created in 2006/2007, plan IT training to carry out this year. | JK |  | Plan day after the survey has been filled in and analyzed. PD day will occur in Sept/Oct 07 – ONGOING, WE WILL PLAN DAY DEPENDANT ON ABILITY FOR THE 19TH OR 26TH OCTOBER 2007. |  |
| 2007/2008 |  |  |  |  |  |
| 5 | Start to implement 4 computers with internet access into each classroom 1-8. |  | JK, GC & LM |  | Focus first on Grade 8 and work down. |
| 7 | Literacy with ICT team each member to buddy up with the same grade teacher (K-6) to help introduce a learning experience. |  | BVW, YD, CB, LL |  |  |
| 8 | Jacqui to lead with all grade 7 & 8 teachers to implement a learning experience with their subject areas. Carrie to act as a reference point. |  | JK & CZ |  | Grade 8’s will be looking at E-Pearl in 2006-2007. |
| 9 | Move from Grade 7 & 8 Computer Studies course taught by Jacqui to allocate those scheduled times for Literacy with ICT for the subject teachers. Subject specific (2 scheduled classes in a 6 day cycle, 1 allocated to Math & Science, the other to ELA & Social), Jacqui to support. Jacqui’s schedule will need to be built around this grade 7 & 8 time so that she is available for support purposes K-8. |  | JK & GC |  |  |
| 2008/2009 |  |  |  |  |  |
| 10 | FULL IMPLEMENTATION |  | ALL |  |  |
| 11 | Lab on Wheels K-8 (15 laptops). There will be a sign out schedule for K-8 to allow easier integration into the regular curriculum. Jacqui will manage and support. |  | JK & GC |  | We will look at Computers for Schools. GC to ask Nora if this could be fundraised. |
| 12 | Computer Lab will be renamed to “The Technology Zone”. |  | JK & GC |  |  |
| WOULD LIKE TO HAVE 4 INTERNET CLASSROOM COMPUTERS K-8. |  |  |  |  |  |

Team Members:

Giuseppi Caligiuri

Jacqui Kroeker

Barb Van Walleghem

Additional Notes: Next Meeting: March 15th, Day 1, Period 4 (11.45). (After the Technology Meeting)