| Literacy with ICT Team Action Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| 2007-2008 |  |  |  |  |
| Action # |  | Action Details | Action Owner | Progress/Completed Yes/No |
| 1 |  | Investigate whether it would be cheaper and more effective to host ePearl using Merlin on our server or combine with Archdiocese of Winnipeg. GC/LM is dealing with this with the overall package from Merlin Part of the Merlin Package. GC will call. | GC/LM | Ongoing |
| 2 |  | All Literacy team members to buddy up with grade level buddy to help expand learning experiences to other teachers. Barb – Susanne Cherly B. – Clare Yoanne – Rosanne Lisa – Carrie Barb spoke with Cheryl B and Yoanne re: buddying up | All | Ongoing |
| 3 |  | Barb and Lisa to attend the Winter Literacy with ICT Workshop on January 31 and February 1, 2008. BVW email Cheryl to confirm both Barb and Lisa will attend. GC to book subs. | LM BVW GC | Completed Ongoing Completed |
| 4 |  | Order from Safe Schools (MISSING) for grades 6, 7 and 8 Barb will ask Cheryl P. at winter session about these posters | LM BVW | Completed |
| 5 |  | Link to Literacy with ICT website from our St. Maurice site. | LM | Completed |
| 6 |  | Link to ePearl on Desktop folder in lab. | LM | Ongoing |
| 7 |  | Request Microphones with headsets. Headsets are $28, LM test on the Windows 2000 machines if they work . Buy 4 more headsets | LM | Completed |
| 8 |  | October 26, 2007 PD Day | All | Completed |
| 9 |  | Organize an information evening for parents and teachers to explain Literacy with ICT - Explain the new curriculum - Explain the new reporting method - Present ePearl to explain student involvement and portfolio use. | GC DW BVW LMM | Ongoing Revisit after February meeting |
| 10 |  | Plan March 2008 PD Day | ALL | Ongoing |
| 11 |  | Discuss reporting Grades 4 to 6 reporting ICT now. When will K to 3 will report? Grades 7 and 8 on hold until next fall. | ALL | Ongoing GC will talk to Dan about all K-6 reporting in February. |
| 12 |  | Start to implement 4 computers with internet access into each classroom 1-8. Focus first on Grade 8 and work down. Each class has at least 2 now. | LM GC | Ongoing |
| 13 |  | Move from Grade 7 & 8 computer studies course to allocate those scheduled times for Literacy with ICT for the subject teachers. Subject specific (2 scheduled classes in a 6 day cycle, 1 allocated to Math & Science, the other to ELA & Social), Lisa to support. Lisa’s schedule will need to be built around the Grade 7 & 8 time so that she is available for support purposes K-8. | GC DW LMM | Ongoing Revisit in 2008 |
| 2008/2009 Implementation Stage |  |  |  |  |
| 14 | FULL IMPLEMENTATION |  | ALL |  |
| 15 | Lab on wheeles 1-8 (15 laptops). There will be a sign out schedule for 1-8 to allow easier integration into the regular curriculum. Lisa will manage and support. We will look at Computers for Schools. GC to ask Nora if this could be fundraised. |  | GC LM LMM | Ongoing Fundraising has been confirmed Hopefully this will happen in Feb/Mar 2008 |
| AIM TO HAVE 4 INTERNET CLASSROOM COMPUTERS K-8 |  |  |  |  |

Team Members:

Giuseppi Caligiuri

Dan Ward

Lisa Martins

Barb Van Walleghem

Additional Notes:

Next Meeting - February 5th, 2008 at 3:35 pm in GC’s office.