St. Emile School Implementation Plan

for LwICT during 2006-07

1. LwICT Implementation Team:

1.1 Composition of our LwICT team

School Administrator: Bill Yaworsky;

Teacher Consultants: Jean W., Paula D., Carol Ann L., Cathy H., Cathy C.,

1.2 Role of our team in LwICT implementation

- Info gathering and sharing to staff at meetings;

- Modeling use of LwICT in the classroom;

- Networking with other schools

- Ongoing PD opportunities; ensuring remaining staff ( 6 remaining) receive foundational training;

- Assume leadership role in assessing and reporting on lwict

- Communication with Board members to ensure they appreciate the ongoing costs related to technology

1.3 Release time for our team this school year to meet and plan and to provide professional learning or mentoring

]

Teacher consultants require 2 days to plan short and long term goals for St.Emile staff ( eg. Report card modifications; letters to teachers/families on new MECY publication; accessing ePearl accounts; creating blog accounts, discussing big ideas and continuums; engaging Parent Council on info evenings for parents etc).

1.4 What tips does your team have for how to structure an effective LwICT implementation team?

- Adequate release time

- Admin support ( eg. Reallocation of funds and re-thinking priorities)

- Provide essential resources/equipment/hardware/software

- Opportunity to network with MECY staff and other schools

2. Professional Learning:

2.1 Schedule and type of professional learning opportunities our LwICT team provided, or are planning to provide, for teachers and school leaders in your division.

- Ensure remaining staff get wait listed for April 23, 24/08 session hosted by MFIS

- Summer Institutes August 12-15 (mentoring teacher leaders); August 19-21; 26-28

2.3 Types of professional learning (face-to-face, by distance, large group, small group, by grade level or snapshot grouping, one-on-one mentoring…)

School based teacher blog focused on teacher action research; MECY PD sessions; team meetings; staff meetings

2.4 Tips our team has for how to structure effective professional learning to support implementation of LwICT

- Stay focused; streamline priorities

- Teacher survey re: present comfort level and support required

- Set and monitor goals and timelines

- Respect deadlines

- Involve staff on all progress made and challenges remaining

3. Implementation Schedule:

3.1 How our teachers have begun to implement LwICT in 2006-07?

Teachers have begun to make changes/adaptations to report cards

3.3 How our school has included LwICT in our school plans

PD priority

3.4 Our projected implementation for 2007-08

All staff inserviced by Fall 2008 in initial implementation; project to use one or two PD days in 2007-2008, inviting MECY to assist us; prepare reporting format for school

3.5 Tips our team has for ensuring an effective schedule for implementation of LwICT

Think in small steps, realistic goals.

4. Connections:

4.1 Other school or divisional initiatives that we are connecting to our implementation of LwICT (ie assessment, curriculum [specify], inquiry, etc).

MFIS, CSC, AWCS (divisional goals).

4.2 Tips our team has for effective connection of implementation of LwICT with existing school and/or divisional priorities

Make it priority, don’t over commit. Set aside PD days and document accordingly.

5. Evidence:

5.1 Evidence we are using to support our reporting of student literacy with ICT (portfolios, eportfolios such as ePearl, student profiles, student/teacher conversations, etc

Grade 8 do Powerpoint portfolios, Grades 6 – 7 post assignments on Homepage, e-mail opportunities from parents; early years portfolios, student led conferences.

6. Reporting:

6.1 When, how, and who in our school has already reported, or are planning to report, to parents on student literacy with ICT? [Please post your EY and MY reporting model(s) in First Class.]

Currently being examined.

6.3 How our reporting on student literacy with ICT is integrated with existing reporting

Currently being examined.

7. Parental Reaction:

7.1 Response we have had from parents about the LwICT implementation and ePearl pilot in our school

Not yet determined

8. Learning Tools:

8.1 Do students in our school have access to their own email?

No, except grades 4 & 6.

8.2 Do students in our school have access to blogs, wikis, and the read/write web?

Yes.