| Literacy with ICT Team Action Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| 2006/2007 |  |  |  |  |
| Action # | Action Details | Action Owner |  | Status |
| 1 | Set up computer lab (Multimedia Center) with 15 work stations. Purchase four multimedia computers from CFS for individual classrooms—KA, KB, Grade 1 and Grade 3. Purchase laptop computers from CFS for all interested staff members. | Bob, Sharon |  | Complete |
| 2 | ICT Coordinator to attend two-day workshop in August, one-half day workshop at St. Maurice and two-day workshop in March. | Sharon |  | Complete |
| 3 | ICT Coordinator to work with all staff to brainstorm ways of integrating technology into their classes | Sharon and teachers |  | Ongoing |
| 4 | Have ePearl accounts set up for Grade 3, 5 and 7 classes. Work with teachers to get student working with their portfolios. | Sharon, Kathy, Colleen, Rosina |  | Started and Ongoing |
| 5 | Appoint ICT team leaders from K-2, Grade 3-5, and Grade 6-8 to work with Sharon to gain an understanding of the Learning with ICT Continuum and pass the information on to their Grade level teams |  | Sharon, Gail, Colleen and Rosina | Team made, meeting date to be determined |
| 6 | Work through jigsaw activity and scavenger hunt with ICT team |  | Sharon | No |
| 7 | Register Gail, Colleen and Rosina in May 2007 ICT workshop through MFIS |  | Bob | Yes |
| 8 | Establish PD/workshop dates for 2007-2008 to work on ICT |  | Bob, Sharon | Yes—Dates: Oct. 2, Jan. 8, April 8 |

| 9 | Plan purchase of one-two Smart Boards, digital video cameras and still camera | Bob, Sharon |  |  | Quotes obtained on Smart Boards, research still to be completed on cameras |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | Assess all teachers for computer literacy using the two surveys available in First class. Use the results to plan workshop content for three dates established for 2007-2008. Survey to be completed by March 23, 2007. | Sharon |  |  | Survey—Yes Workshop planning--No |  |
| 11 | ICT to meet to come up with Reporting model for use in fall 2007. | Bob, Sharon, Gail, Colleen and Rosina |  |  | No |  |
| 2007/2008 |  |  |  |  |  |  |
| 12 | Expand computer lab by adding 15 more computers. Purchase four multimedia computers from CFS to be placed in classrooms—Grade 2, Grade 4, Grade 5 and Grade 6. Purchase laptops for interested staff members from CFS. |  |  | Bob, Sharon |  | No |
| 13 | Contact Merlin to establish cost of hosting ePearl accounts. Introduce ePearl to Grade 3, 5 and 7 students and continue accounts for Grade 4, 6 and 8 students. |  |  | Bob, Sharon and Grade 3-8 staff |  | Yes |
| 14 | ICT in-servicing for Staff—three dates for this school year. 1st inservice complete—reconstruction of continuum and introduction to learning resources on Manitoba Education website |  |  | All staff |  | On-going |
| 14 | Work on Reporting model for use in Spring 2008—model is not ready for Fall 2007 |  |  | Staff |  | No |
| 2008/2009 |  |  |  |  |  |  |
| 14 | FULL IMPLEMENTATION |  | All staff |  |  |  |
| 15 | Lab on Wheels |  | Bob, Sharon |  |  | No |
| 16 | Purchase four multimedia computers from CFS for Grade 7 and 8 classrooms. |  | Bob, Sharon |  |  | No |

Team Members:

Bob Morrison, Sharon McRae, Gail Aguair, Colleen Laufer, Rosina McClintock