| Literacy with ICT Team Action Plan |  |  |  |  |
| --- | --- | --- | --- | --- |
| 2006/2007 |  |  |  |  |
| Action # | Action Details | Action Owner |  | Status |
| 1 | Set up computer lab (Multimedia Center) with 15 work stations. Purchase four multimedia computers from CFS for individual classrooms—KA, KB, Grade 1 and Grade 3. Purchase laptop computers from CFS for all interested staff members. | Bob, Sharon |  | Complete |
| 2 | ICT Coordinator to attend two-day workshop in August, one-half day workshop at St. Maurice and two-day workshop in March. | Sharon |  | Complete |
| 3 | ICT Coordinator to work with all staff to brainstorm ways of integrating technology into their classes | Sharon and teachers |  | Ongoing |
| 4 | Have ePearl accounts set up for Grade 3, 5 and 7 classes. Work with teachers to get student working with their portfolios. | Sharon, Kathy, Colleen, Rosina |  | Started and Ongoing |
| 5 | Appoint ICT team leaders from K-2, Grade 3-5, and Grade 6-8 to work with Sharon to gain an understanding of the Learning with ICT Continuum and pass the information on to their Grade level teams |  | Sharon, Gail, Colleen and Rosina | Team made, meeting date to be determined |
| 6 | Work through jigsaw activity and scavenger hunt with ICT team |  | Sharon | Complete |
| 7 | Register Gail, Colleen and Rosina in May 2007 ICT workshop through MFIS |  | Bob | Yes |
| 8 | Establish PD/workshop dates for 2007-2008 to work on ICT |  | Bob, Sharon | Yes—Dates: Oct. 2, Jan. 8, April 8 |

| 9 | Plan purchase of one-two Smart Boards, digital video cameras and still camera | Bob, Sharon |  |  | Quotes obtained on Smart Boards, research still to be completed on cameras—Purchased video camera. |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | Assess all teachers for computer literacy using the two surveys available in First class. Use the results to plan workshop content for three dates established for 2007-2008. Survey to be completed by March 23, 2007. | Sharon |  |  | Survey—Yes Workshop planning--No |  |
| 11 | ICT to meet to come up with Reporting model for use in fall 2007. | Bob, Sharon, Gail, Colleen and Rosina |  |  | On-going |  |
| 2007/2008 |  |  |  |  |  |  |
| 12 | Expand computer lab by adding 15 more computers. Purchase four multimedia computers from CFS to be placed in classrooms—Grade 2, Grade 4, Grade 5 and Grade 6. Purchase laptops for interested staff members from CFS. |  |  | Penny, Sharon |  | Yes |
| 13 | Contact Merlin to establish cost of hosting ePearl accounts. Introduce ePearl to Grade 3, 5 and 7 students and continue accounts for Grade 4, 6 and 8 students. All students from K to 8 have ePearl accounts. |  |  | Penny, Sharon and Grade 3-8 staff |  | Yes |
| 14 | ICT in-servicing for Staff—three dates for this school year. 1st inservice complete—reconstruction of continuum and introduction to learning resources on Manitoba Education website. Second inservice complete and was based on sharing of ICT activities at various grade levels. Assessment was also discussed. |  |  | All staff |  | On-going |
| 15 | Work on Reporting model for use in Spring 2008—model is not ready for Fall 2007. Work towards Reporting in Spring 2009. |  |  | Staff |  | No |
| 16 | Internet access in all classrooms |  |  | Sharon |  | No |
| 17 | Purchase a Smartboard for computer lab. |  |  | Penny, Sharon |  | No |
| 18 | Purchase digital cameras for each classroom. |  |  | Penny, Sharon |  | No |
| 2008/2009 |  |  |  |  |  |  |
| 19 | FULL IMPLEMENTATION |  | All staff |  |  |  |
| 20 | Lab on Wheels |  | Penny, Sharon |  |  | No |
| 21 | Purchase four multimedia computers from CFS for Grade 7 and 8 classrooms. |  | Penny, Sharon |  |  | No |
| 22 | Time allotment for working on reporting model for Spring 2009 |  | ICT Team members and Grade level groups |  |  | On-going |
| 23 | Purchase of portable Smartboards and projectors for each floor of the school. Ex. K level, Gr1-3 level, Gr. 4-5 level and Gr. 6-8 level and computer room |  | Penny, Sharon |  |  | No |
| 24 | Continue partnership agreement with Merlin. |  | Penny, Sharon |  |  | No |

Team Members:

Bob Morrison (2006-2007), Dr. Penny (2007), Sharon McRae, Gail Aguair, Colleen Laufer, Rosina McClintock